## Slide 1: Strategic Plan Update
Q3 Academic Year 2017-18 (January – March 2018)

## Slide 2: Year 3 Initiatives
Enrollment
  Deliver Strategic Enrollment Plan by December 2017
  Deliver Academic Master Plan by April 2018
  Deliver new intentional advising and student success model and system serving at least 2,400 first- and second-year students per year – beginning in Fall 2017
  Deliver proposals for four new degree programs in FY2018
  Deliver Systemic Technology Review by April 2018
Strengthen Governance & Foster Community
  Deliver Leadership Training Program for 50 employee participants by Spring 2018
  Deliver better internal communications with
    Monthly face-to-face institution-wide directors’ meeting starting September 2017
    New Intranet by March 2018
Leverage Resources & Increase Revenue
  Deliver outreach to secure diversified revenue:
    Continue first Capital Campaign in a decade
      12% increase in fundraising for needs-based scholarships in FY18 over FY17
      Secure multi-million-dollar gift to fund a center to help first-generation students
    Launch grant writing infrastructure
    Seek funding from the 2018 General Assembly for FY19
      $1.8 million to support sector change
      $4.9 million for statewide aviation growth
      $12.7 million for major capital improvements in Cochran
Enhance Service to Students
  Deliver 75% of Student Affairs programming aligned to Student Engagement model
    Guide 100 students to Bronze certification in Experiential Learning
  Deliver Comprehensive Housing Plan wi9th alternatives to P3 and living-learning communities for implementation and launch in Fall 2018

## Slide 3: Year 3 Initiatives Progress
Chart: Percent Complete
| 10) Comprehensive Housing Plan | 9b) 100 Bronze-level EL Certifications | 9a) Student Affairs Programming Aligned to Student Engagement Model | 8c) Diversified Revenue - General Assembly Funding | 8b) Diversified Revenue - Grant Infrastructure | 8a) Diversified Revenue - Capital Campaign | 7b) Better Internal Communcations - Intranet | 7) Better Internal Communications - Face to Face | 6) Leadership Training | 5) Systemic Technology Review | 4) New Programs | 3) Advising System | 2) Academic Master Plan | 1) Strategic Enrollment Plan
Percent Complete | 90 | 75 | 100 | 75 | 50 | 50 | 90 | 100 | 60 | 50 | 75 | 85 | 100 | 100

## Slide 4: Detailed Updates

## Slide 5: Progress in Focus on Enrollment
Chart: Percent Complete
| 5) Systemic Technology Review | 4) New Programs | 3) Advising System | 2) Academic Master Plan | 1) Strategic Enrollment Plan
Percent Complete | 50 | 75 | 85 | 100 | 100
Enrollment Action Plan delivered to USG Chancellor in January. Marketing, recruitment, implementation of enrollment consultant recommendations underway. Ad Hoc Retention, Progression, and Graduation Committee being convened.
Academic Identity and Strategy published in February, analysis of Programs by Location completed in March, new Structure and Assignments in Office of the Provost effective April 1.
Academic Affairs working with each department, college, or school to develop advising frameworks, which will provide an advisor for every student (some professional, some faculty) who will guide a student from the time they first step foot on campus (or login, if an online student) through graduation.
Proposal for BS in Political Science submitted to USG. Proposal for MS in Social Work still under consideration. Administrative approval for AS in Health Science was granted by USG. BS in Rehabilitative Science under development.
While a technology strategy will be developed as part of the next Strategic Plan, a Systemic Technology Review looking at how we manage $400K worth of technology, setting a strategic direction for the Center for Excellence in Teaching and Learning, identifying types of data and systems needed, and determining the viability of data warehouse is underway.

## Slide 6: Progress on Strengthen Governance & Foster Community
Chart: Percent Complete
| 7b) Better Internal Communcations - Intranet | 7a) Better Internal Communications - Face to Face | 6) Leadership Training
Percent Complete | 90 | 100 | 60
27 employees have nearly completed training on which we partnered with Columbus State’s Leadership Institute. Planning for internal training on topics such as interviewing is underway, which will serve another 23 employees.
a) Monthly face to face meetings among directors across all units began in October. Spring meetings scheduled through May.
b) Prototype designed and developed. Significant updates made to Faculty & Staff dashboard on mga.edu, including password protected features, OneDrive launched. Additional link to be sent to employees this month requesting feedback.

## Slide 7: Progress on Diversified Revenue
Chart: Percent Complete
| 8c) Diversified Revenue - General Assembly Funding | 8b) Diversified Revenue - Grant Infrastructure | 8a) Diversified Revenue - Capital Campaign
Percent Complete | 75 | 50 | 50
a) Approximately 13% increase obtained in need-based scholarship funds awarded. Capital campaign funds raised stand at approximately 25% of multi-year goal. Multi-million ask in progress, with additional prospects in the pipeline.
b) Acquired and installed grant lead software. Created and staffing grant writer position. Candidate interviews underway.
c) Request for $3.2 Million awaiting USG and Governor action following 2018 Legislative Session.

## Slide 8: Progress on Enhance Service to Students
Chart: Percent Complete
| 10) Comprehensive Housing Plan | 9b) 100 Bronze-Level EL Certifications | 9a) Student Affairs Programming Aligned to Student Engagement Model
Percent Complete | 90 | 75 | 100
a) All programs delivered in 2017-18 support the categories of the Student Engagement model:
  Life skills
  Wellness
  Service learning
  Community building
  Diversity
  Scholarship
9) b) The number of students who have received the following certifications due to Student Affairs programs/events:
  Bronze – 54
  Silver – 14
  Gold – 3
  Platinum – 1
Written Housing Plan delivered in Q2. Living Learning Communities under final development, with three (one offered in both Macon and Cochran for a total of four available) to launch in Fall 2018.