## Slide 1: Strategic Plan Update
Year End update (July 2016 – June 2017)

## Slide 2: Executive Summary
Growth
  1 action items complete
  3 action items in process
Students
  6 action items complete
People
  4 action items complete
  1 action item in process
Fiscal
  3 action items and 1 sub-item complete
  1 sub-item in process
Knowledge
  1 action item complete
  4 sub-items in process

## Slide 3: Growth
Chart: Percent Complete
| 4) Program Accreditation | 3) Graduate Programs | 2) Enrollment Plan | 1) Academic Plan
Percent Complete | 30 | 100 | 80 | 80

## Slide 4: Students
Chart: Percent Complete
| 9) VECTR | 8) Knowledge@Work | 7) Study Abroad | 6) NAIA 5-Star | 5b) Student Leadership | 5a) New Program Model
Percent Complete | 100 | 100 | 100 | 100 | 100 | 100

## Slide 5: People
Chart: Percent Complete
| 14) Institutional Policies | 13) Diversity | 12) Leadership Training | 11) Climate Survey | 10) FLSA
Percent Complete | 100 | 100 | 50 | 100 | 100

## Slide 6: Finances
Chart: Percent Complete
| 17) Legislative Relations | 16b) Fac/Staff Campaign | 16a) Campaign Proposals | 15b) Decentralized Budget | 15a) New Budget Model
Percent Complete | 100 | 100 | 100 | 50 | 100

## Slide 7: Knowledge
Chart: Percent Complete
| 20) University Advisory Board | 19) AA Advisory Boards | 18c) Measure Performance | 18b) Student Service | 18a) Data-driven decisions
Percent Complete | 100 | 75 | 75 | 90 | 90

## Slide 8: Detailed Updates

## Slide 9: Academic Affairs (Growth)
Academic Master Plan |  |  | 
Task | Lead | Start Date | Notes
Market Demand Analysis | Institutional Research | 10/3/16 | Matriculate data, DoL and local business interviews completed.
Internal Stakeholder Focus Groups | Institutional Research | 6/25/17 | Initial groups identified, groups being scheduled.
Academic Inventory | Vice-Provost Academics | 9/1/17 | Completed
Modeling of at-risk students | Institutional Research | 3/1/17 | Data being collected
Create Center of Excellence in Teaching | Vice-Provost Academics | 1/3/17 | Center design completed Announce at convocation
Program Development | Academic Deans | On-going | Respiratory Therapy and Music submitted to USG
Accreditation Feasibility | Academic Deans | 10/3/16 | AACSB review ongoing

## Slide 10: Academic Affairs (Growth)
Graduate Programs |  |  | 
Task | Lead | Start Date | Notes
Increase enrollment by program | Academic Deans/ Graduate Dean Enrollment Management | 8/15/16 | Earlier outreach by advising to admitted students
Launch MSM, MAT | Academic Deans Graduate Dean | Spring launch – MSM Summer launch – MAT | Completed
Track retention and graduate rates | Academic Deans Institutional Research | 8/15/16 | Retention strategies ongoing
New Program Development | Academic Deans Graduate Dean | 1/3/17 | MSW, BS OTA, Certificate Analytics, BS Engineering Tech under review

## Slide 11: Academic Affairs (Students)
Support/Engage |  |  | 
Task | Lead | Start Date | Notes
Study abroad participation | Director, International Programs | 8/15/16 | 29 are in Europe over summer 26 students traveled to Dominican Republic
Exchange program | Director, International Programs | 8/15/16 | Hosted first student from Northampton University
Knowledge@Work | Director, QEP | 8/15/16 | 200 students graduated with K@W credential Created “Platinum” status

## Slide 12: Academic Affairs (Knowledge)
Support/Engage |  |  | 
Task | Lead | Start Date | Notes
Create data warehouse | Vice-Provost, Quality Director, IR | 8/15/16 | Warehouse installed, Created prototype executive dashboards
Dashboards | Institutional Research |  | Presidential Dashboards provided weekly. New dashboards piloted.
Establish data governance committee/policies | Vice-Provost, Quality Director, IR | 1/9/17 | Committee will meet in Fall 2017
Faculty scholarship and creativity | Academic Deans | 8/15/16 | 9 books/articles, 15 presentations, $120K grants, 29 talks and performances
Process-Mapping of academic processes | Vice-Provost, Academics | 8/15/16 | System-wide communication plan created

## Slide 13: Fiscal Affairs (People)
Invest in Employees |  |  | 
Task | Lead | Start Date | Notes
Disseminate information on changes for FLSA | Executive Director, HR | 8/15/16 | Completed
Implement changes for payroll and overtime | Executive Director, HR | 8/15/16 | Completed
Create working group on climate survey issues | Executive Director, HR | 8/15/16 | Completed, group presented to Cabinet
Identify top issues from climate survey to address | Executive Director, HR | 1/3/17 | Issues being prioritized
Leadership training | Executive Director, HR | Move to Fiscal Year 2018 | Under evaluation

## Slide 14: Fiscal Affairs (Finances)
Budget Processes |  |  | 
Task | Lead | Start Date | Notes
Develop potential budget models | Executive VP, Finance | 8/15/16 | Scenarios presented to USG at January USG Budget Hearing Allocations from USG received and distributed to divisions
Decentralized budget model | Executive VP, Finance | 11/15/15 | Collaborative budget process implemented with Cabinet Increased communication with University on budgetary items established

## Slide 15: Student Affairs (Students)
Support/Engage students |  |  | 
Task | Lead | Start Date | Notes
New programming model Life skills Wellness Service Learning Diversity Community building | Director, Student Engagement | 8/15/16 | Pilot programs offered and were successful
Student Leadership conference | Director, Student Engagement | 11/1/16 | Completed
NAIA 5 Star Champions of Character | Director, Athletics | 8/15/16 | Attained Silver status

## Slide 16: Student Affairs (People)
Engage Faculty/Staff |  |  | 
Task | Lead | Start Date | Notes
Diversity Ad Hoc committee recommendations | Director, Diversity | 8/15/16 | Recommendations submitted to Faculty Senate and approved
Communication plan | Director, Diversity | 10/1/16 | Plan to create web presence and use of social media is built
Institutional Diversity and Inclusion Conference | Director, Diversity | 2/1/17 | Plan has been created

## Slide 17: University Advancement (Finances)
Engage Faculty/Staff |  |  | 
Task | Lead | Start Date | Notes
Campaign planning | VP, University Advancement | 8/15/15 | Priorities, timeline and amount approved by foundation
Identify top prospects | VP, University Advancement | 8/15/16 | Campaign cabinet and Chair selected Prospects identified
Proposal submission | VP, University Advancement | 8/15/16 | 7-figure proposals were submitted 1 is under review 1 pledge for $1M
Faculty/Staff campaign | VP, University Advancement | 8/15/16 | Completed Raised $80,310 (8.8% increase from last year)

## Slide 18: Recruitment & Marketing (Growth)
Plan and Assess |  |  | 
Task | Lead | Start Date | Notes
Evaluate promotional strategies | VP, Recruitment & Marketing | 9/1/16 | Analysis of several areas complete, along with ROI. Adjustments made.
Evaluate yield across the funnel | VP, Recruitment & Marketing | 8/1/16 | Re-evaluated and revising communications plan
Recruiting strategies across major student segments | VP, Recruitment & Marketing | 8/15/16 | New strategies and goals in place
Lead in the development of a strategic enrollment plan | VP, Recruitment & Marketing | 9/1/16 | Capacity study underway with recommendations expected 9/30/17

## Slide 19: Office of the President
Engage Stakeholders |  |  | 
Task | Lead | Start Date | 
Strengthen Institutional Policies | Compliance Commission University Counsel | 7/1/16 | Twelve policies created or updated this academic year
Legislative Relations | President Chief of Staff | 8/15/16 | Second phase of funding for Aviation Strategic Plan secured
University Advisory Council | President Chief of Staff | 8/15/16 | Council empaneled, first meeting held on May 12
Georgia VECTR Center | University Counsel VECTR Executive Director | 8/1/16 | Successful launch, operations for FY17, and transition to TCSG for FY18
Campus Affairs | University Counsel Campus Directors | 7/1/16 | Services to commuter campuses improved, new facilities use process in place
Presidential Communications | President University Counsel | 7/1/16 | Issued first President’s Annual Report, frequency of blog posts increased